## Sheet1
Milestone | Task | Description | Duration
Milestone 1 | Project Setup and Basic Server-Client Communication |  | 1 Week
| 1.1 Project Initialization | Set up a C++ project using an IDE (e.g., Visual Studio). Initialize a Git repository for version control.
| 1.2 Server-Client Communication | Implement a basic server and client using socket programming. Establish a connection between the server and client. Implement basic message sending and receiving.
Milestone 2 | User Authentication |  | 3 Days
| 2.1 User Database | Set up a simple user database or data structure to store user credentials (e.g., usernames and passwords).
| 2.2 User Registration and Login | Implement user registration functionality where users can create accounts. Implement user login functionality with username and password verification.
Milestone 3 | Chat Features |  | 2 Days
| 3.1 User List | Create a list of online users on the server. Update the list in real-time as users log in and out.
| 3.2 Private Messaging | Implement one-to-one private messaging between clients.
| 3.3 Group Chat | Implement group chat functionality where users can create and join chat groups.
Milestone 4 | Robustness and Error Handling |  | 2 Days
| 4.1 Error Handling | Implement error handling for various scenarios, such as connection loss, incorrect login credentials, etc.
| 4.2 Multi-Threading | Use multi-threading to handle multiple client connections concurrently.
Person
Anas
Divyaraj
Anas
Divyaraj
Anas
Divyaraj
Anas
Divyaraj